## Stakeholder Map
Stakeholder | Category | Priority | Status | Date Contacted | Internal Assignee | External POC(s) | VSU Role | Project Role | Financial Ask | In-Kind Ask | Stakeholder Goal | Mutual Goal | Pushback / Risk | Decision Needed | Open Questions | Research Depth | Next Step
Dominion Energy | External — Funding | Now — well-researched, clear next step (Woomer); reach out immediately | Not Yet Contacted | Not Yet Contacted | Dr. Nicholson | James Beazley (State Government Affairs Executive, VGR Secretary); Joe Woomer (VP Dominion Energy, School of Business Management & Marketing Advisory Council); Daniel Holmes (Technical Specialist II, Dept. of Engineering Industrial Advisory Council) | None | TBD | Cash funding (grant or sponsorship) — amount not yet specified | Mentors, guest lecturers, pitch day support/judging | Talent pipeline for energy data analytics + business intelligence. Needs graduates who can interpret sensor data and translate it into business decisions. | VSU students trained to assemble sensors, collect data, interpret it, and present findings — skills Dominion needs for data-to-decision roles. | 1) May be more interested in engineering talent than entrepreneurship. 2) May be more interested in business intelligence than business generalists. 3) Fall grant cycle timing may not align with January launch. | Which contact to lead with — Woomer is VP-level and business-facing (likely strongest entry), vs. Beazley or Holmes. Pending Nicholson's decision and conversation with Beazley. | Does Dominion's fall grant-cycle timing actually allow funds to land before our January launch, or is this really a Year 2 conversation for them too? Would the business/decision-intelligence angle matter to Dominion, or are they purely focused on engineering talent — what would they actually want to get out of the students? | Well-scoped | Formal follow-up via one or more of the three named contacts — Woomer likely strongest entry point given program is business-student-facing.
Deloitte | External — Funding | Deprioritized — won't fund an unproven pilot; unclear why they'd prioritize an HBCU program specifically | Not Yet Contacted | Not Yet Contacted | Javon | Chastity Gore (Campus Recruiter, Atlanta); Christina McCoy (Advisory Manager, Norfolk); Jason Young (Partner, Arlington); Pat Fernandez (Richmond); Tiffany Palmer (Newport News); Donovan Gayles (Arlington). Campus recruiters are the only realistic entry point in Year 1–2. | None | TBD | $5,000–$10,000 sponsorship for branded materials, student hardware kits, and one cohort-wide career workshop. Do NOT ask for stipends or operational funding — Deloitte does not fund unproven pilots. | ONE campus recruiter (e.g. Chastity Gore) to deliver a 90-minute virtual 'What Deloitte Looks For' session and attend Career Day as a judge only (2 hrs max) — not ongoing mentors/weekly coaches. Also: coordinate field trips to Deloitte's Richmond, Virginia Beach, and Northern Virginia offices. | 1) Build a direct pipeline to skilled, tech-enabled talent trained on the tools/approaches Deloitte uses with incoming analysts. 2) Access students who understand real-world business problems and Deloitte-style casework, reducing onboarding time. 3) Align with strategic growth areas — digital transformation, innovation, sustainability, generative AI. | 1) We secure funding for operations/materials — Deloitte builds a pipeline to skilled talent. 2) We secure judges/coaches/mentors — Deloitte gets early access to job-ready students. 3) Field trips to VA offices — Deloitte deepens regional brand visibility in key VA markets. | 1) Students learn to prompt, not to problem-solve — if they can't code without AI, they can't debug when it fails. 2) One week each on hardware setup/integration is a tour, not real technical depth — can't troubleshoot a real client IoT deployment. 3) Heavy AI reliance across every deliverable (firmware, screens, diagrams, copy) risks teaching AI dependency, not the judgment/critical thinking Deloitte says it wants. 4) No track record yet — Deloitte will ask for GPA, retention, and case-interview performance data before funding. 5) Recruiters have 50+ target schools and thousands of applicants; hard sell that they'll commit to a 14-week observation model for one non-target school. 6) No IP ownership clause — Deloitte won't engage without clarity on who owns student-built work (VSU/student/Builder Tech) before they'd use it for case studies or client work. 7) Deloitte Consulting has no hardware-engineering practice — ESP32/breadboard skills don't map to the roles they actually hire for (strategy, AI analysts, systems integrators). 8) Scalability question — 40-60 students at one regional HBCU reads as a drop in the bucket against global hiring needs; they'll ask if this replicates to 500 students / 10 schools. 9) 'We don't sponsor unproven pilots' — likely ask to run Year 1 without them and return with completion/placement data for Year 2. 10) Partners/senior managers bill $500-1,200/hr — unlikely to commit real time to mentoring or live judging; a recorded pitch video review is the realistic ceiling. Bottom line: pushback will center on skill depth, AI dependency, scalability, and lack of proven outcomes — not the mission. |  | Beyond the recruiting-pipeline value, why would Deloitte prioritize supporting an HBCU program specifically — what's the actual motivation or incentive for them to say yes here? | Well-scoped | Contact former colleagues in VA offices + reach out to the StepUp pro bono team. (Updated Aug 4 — Javon)
Siemens | External — Funding | Now — in progress, awaiting Aug 7 meeting outcome; reach out immediately | In Progress | Not Yet Contacted | Andrew | Gail Norris (Director, SITRAIN Digital Industries Learning — Siemens workforce dev) | Department of Engineering Industrial Advisory Council (IAC) | TBD | Entry-tier cash grant, $5K–$25K — Siemens Foundation's own entry range, explicitly NOT their $100K+ established-partner tier and not comparable to Jabil's $1.1M/3-year commitment. | Mentorship — engineer/mentor time, guest speakers, possibly training content; Gail Norris's own Sitrain/Digital Industry Academy role is a natural fit. Lead with in-kind as the easier first 'yes'; cash as a real add, not an afterthought. | Siemens Foundation's public giving focus is workforce development/STEM career awareness (healthcare, clean energy) — no explicit AI/IoT/open-source language found. Existing real relationship: 2014 announcement of $1B+ in-kind software grants to VA schools, with VSU specifically receiving $105.6M in software across six programs, tied to supporting Newport News Shipbuilding. VSU is also a CCAM partner alongside UVA and Virginia Tech. Typical grant pattern: ~$6.9–7M distributed annually across only ~14–20 grants ($5K–$1.3M+), flowing through ongoing relationships, not open applications. | This program is a single-semester 'toe-dip' exposure play, not a certification/engineering pipeline — explicitly not competing with Siemens' existing $105.6M VSU relationship. It extends the same digital-manufacturing/IoT thread Siemens already invests in at VSU (Newport News smart-shipyard/Teamcenter PLM/digital-twin work is genuinely Industrial IoT in substance) as a light, complementary awareness layer feeding the same regional talent pipeline. |  | Awaiting the Aug 7 cross-party meeting to confirm preferred path: request Dr. Nicholson introduce Gail Norris via VSU's Engineering Dept./Dean Haile, vs. direct cold-call fallback (Siemens Newport News office, +1 757-591-6600, Academic Programs Coordinator) — fallback is unblocked and can run in parallel regardless of meeting outcome. | Who is Andrew's contact at Siemens, and what role do they play there? Do we already have an existing relationship with Gail Norris, or would this be a cold introduction? Siemens appears mostly focused on manufacturing/engineering talent — would they have any interest in computer science or business students, or is this squarely an engineering-only ask? | Well-scoped | Awaiting Aug 7 cross-party meeting outcome; direct cold-call fallback open in parallel.
Apache | External — In-Kind | Medium — needs a named liaison before this can move | Not Yet Contacted | Not Yet Contacted | Andrew | None named yet — VoltPop's own longstanding ASF affiliation is the practical entry point. | TBA — no confirmed individual/role yet | TBA — no confirmed individual/role yet | None identified yet | Guest speaker and stickers/swag for students to start; more specific asks likely once outreach begins — consistent with how the Siemens/Jabil/Huntington Ingalls cluster has been approached (in-kind/mentorship-first). | No individual found holding a role at both ASF and OpenAI/Anthropic, and no 'Anthropic Brand Ambassador' tied to ASF specifically. A real, current institutional relationship exists: Anthropic donated $1.5M to ASF (announced 2026-04-07), and the two orgs separately coordinated on launching an 'ASF Responsible AI Initiative' (per ASF board minutes, May 2026). ASF's own motivation for funding a university program isn't independently established — the angle rests on the Anthropic relationship, not a stated ASF education-giving program. | This program relies almost entirely on free/open-source tooling — a direct 'we're built on your tooling' narrative aimed at ASF, the same dependency story used for Claude for Education/Claude Corps aimed at Anthropic. | No named liaison identified despite the $1.5M donation announcement and board minutes. | Identify an actual liaison on ASF's side — use VoltPop's own ASF affiliation as the entry point to ask internally who'd own this. | Does VoltPop's ASF affiliation actually surface a named contact with real decision-making power? Is there an ASF education-giving budget independent of Anthropic, or does any ask ride entirely on Anthropic's $1.5M donation and goodwill? | Partial — needs a named contact | Identify an actual liaison via VoltPop's ASF affiliation.
Cameron Foundation | External — Funding | Year 2 — next realistic LOI window is Jan 6, 2027, which lines up better with a Year 2 ask anyway | Not Yet Contacted | Not Yet Contacted | Dr. Nicholson | TBA — no named contact identified yet | TBA | Funder only | Cash funding — amount not yet specified | None — funder role only, no in-kind ask | Petersburg, VA-based — service area is literally the Tri-Cities footprint this program is built around. Public funding-interest categories: Health Care, Community & Economic Development, Human Services, Education, Historic Preservation & Conservation, Arts & Culture — no explicit AI/IoT/open-source language, but real STEM-education funding precedent and an exact geographic match. | Regional-employer-pipeline framing shared with Virginia Gateway Region: both connect students to the region's existing large employer base and are geographically anchored to the Tri-Cities/Petersburg footprint specifically — one shared deck concept covers both, swapping name/logo. | Cycle timing doesn't fit our launch: Cameron runs two annual cycles — LOI Jan 6 / Proposal Feb 27 / Award June, and LOI May 1 / Proposal June 25 / Award October. Both 2026 cycles are already closed, so the next realistic entry point for a first-time applicant is the Jan 6, 2027 LOI deadline, leading to a possible award around June 2027 — roughly 10-11 months out. We would need funding outside their regular cycles to hit our timeline, and it's unclear whether they do that often (worth confirming directly rather than assuming). Also unconfirmed: general grants require an all-volunteer governing board of 5+ unrelated people with no paid staff as voting members — if Builder Tech LLC is the applying entity rather than VSU or a 501(c)(3) partner, this could be a disqualifier worth checking before investing more time here. | Ask Cameron directly whether off-cycle/exception funding is something they do, and how often — don't assume based on the published LOI/Proposal/Award calendar. Also confirm who the eligible applying entity would be (Builder Tech LLC vs. VSU vs. a nonprofit partner) given their governing-board eligibility rule. | Does Cameron ever grant outside its published cycle, or is January 2027 genuinely the earliest option? | Needs work — no contact, ask not yet developed | Source a named contact and begin outreach — currently the strongest single lead on the regional-foundation side given the exact geographic match and accessibility (not invitation-gated, unlike Jabil's foundation).
Virginia Gateway Region | External — Facilitator | Medium — pending Nicholson's discretionary-fund question | Not Yet Contacted | Not Yet Contacted | Dr. Nicholson | TBA | TBA | TBA | Not a direct-cash ask. VGR's real funding mechanism is coordination toward third-party grants (GO Virginia Region 4 collaborative grants, VIPC, DHCD) and locality-run micro-business grants (e.g., Prince George County's up to $25,000 program) — not funds VGR holds itself. | Help secure funding/introductions elsewhere (e.g., a warm intro to Beazley/Dominion) and, longer-term, potentially co-build a GO Virginia application once the program has a track record and multi-locality partners to point to. VGR also explicitly offers labor market analysis, commercial market analysis, and customized research as concrete in-kind services — could be used at no cost for program planning/pitch materials. | VGR is a regional economic-development nonprofit, not a CSR/philanthropic grant-maker — its real funding wins are large state/federal site-infrastructure and job-creation grants (e.g., $11.5M Business Ready Sites, $53M EDA regional-challenge grant), not discretionary checks to a single university program. Its actual mission is regional business-readiness and building the local employability pipeline. | This program directly exposes VSU students to real regional employers and feeds a local talent pipeline — squarely the outcome VGR exists to produce, even though it doesn't match VGR's own technical-skills content (manufacturing/supply-chain certs). VSU is already one of VGR's five regional partner institutions — lead with that existing relationship. |  | Does Nicholson have first-hand knowledge of any discretionary sponsorship/community fund at VGR outside the big infrastructure grants (via his personal relationships with James Beazley and Tom Stansbury), or is facilitation really the realistic ask? Needs confirming before finalizing how VGR is pitched. | What are VGR's priorities right now, and how would they actually support this program? We haven't done enough research yet to answer this. Separately: can VGR make a direct introduction to Jabil (352 new jobs, Prince George County, opening fall 2026, secured with VGR's help) as a potential guest-speaker/employer-partner for the cohort, given it's a brand-new employer in VGR's own footprint? This is separate from and in addition to the existing discretionary-fund question tasked to Nicholson. | Partial — mission understood, funding mechanism unconfirmed | Nicholson to confirm discretionary-fund question above.
Open Trellis | External — Unscoped | Low — needs full research before any outreach | Not Yet Contacted | Not Yet Contacted | Dr. Nicholson | Dale Fickett (CEO & Co-Founder, Open Trellis; associated with RVA Works) |  | CEO & Co-Founder | Not yet researched | Not yet researched | Not yet researched | Not yet researched | Open Trellis could potentially be a competitor rather than a partner — not yet confirmed either way, needs more research before outreach. | Full research needed — currently just a name and title. | What does Open Trellis/Dale Fickett's organization actually do, and does it overlap with this program in any way — funding, mentorship, something else? Is the RVA Works affiliation relevant to VSU or the Tri-Cities specifically, or is that a different region entirely? | Needs work | Share with Internal Assignee and populate initial columns. (Updated Aug 4 — Javon)
Center for Entrepreneurship | Internal — VSU | Medium — internal, needs contact + research | Not Yet Contacted | Not Yet Contacted | Dr. Nicholson | TBA — Nicholson has contact(s), not yet added | VSU — Center for Entrepreneurship |  | Not yet researched | Not yet researched | Not yet researched | Not yet researched |  | Nicholson to add named contact(s); needs full research on motivations and what a reasonable ask looks like. | What has the Center for Entrepreneurship specifically told Nicholson their goal is? | Needs work
College of Engineering and Technology | Internal — VSU | High — active contact (Dean Haile), can move now | Not Yet Contacted | Not Yet Contacted | Dr. Nicholson | Dr. Dawit Haile | VSU — School of Engineering (Dept. of Engineering Industrial Advisory Council) | TBA | Not a funding ask — open, unconfirmed idea that this College and Reginald F. Lewis College of Business could split the program's core cost between them, with external funding landing on top. | Institutional buy-in: legitimacy/endorsement, curriculum integration (credit-bearing status, class time), physical/logistical lab and classroom access, faculty/dean bandwidth, administrative unblocks (FERPA 'school official' designation, background-check sign-off, indemnification/liability language). | Not yet researched from the College's own side — no positions or concerns from Dean Haile captured beyond his role as an active, already-coordinating contact. | An existing MoU already mandates CoET/Business collaboration — this is closer to activating a standing agreement than starting one from scratch. Program offers student outcomes, employer-pipeline value, and program prestige for the college. |  | Confirm with Dean Haile whether the cost-split idea with the Business College is viable. | What goals does the School of Engineering have that aren't already being met — i.e., that they don't already have projects in the pipeline addressing? | In progress | Dean Haile is a known, already-coordinating contact — can move now. Still needs its own dedicated hosting-focused pitch (distinct from every funder-facing deck).
Reginald F. Lewis College of Business | Internal — VSU | Probably High — blocked until incoming dean starts (mid-Aug 2026), but same MoU-activation logic as CoET suggests strong fit once unblocked | Blocked | Not Yet Contacted | Dr. Nicholson | TBA — Nicholson has contact(s), not yet added | VSU — Reginald F. Lewis College of Business | TBA | Not a funding ask — same open cost-split idea as College of Engineering and Technology. | Same institutional buy-in list as College of Engineering and Technology: legitimacy/endorsement, curriculum integration, lab/classroom access, faculty/dean bandwidth, administrative unblocks. | Not yet researched — no dean in place to ask yet. | Same MoU-activation logic as College of Engineering and Technology — student outcomes, employer-pipeline value, program prestige. |  | Blocked until the incoming dean starts (mid-August 2026) — no one to confirm anything with yet. | What goals does the Business school have that aren't already being met — i.e., that they don't already have projects in the pipeline addressing? | Blocked | Wait for incoming dean (mid-August 2026).
Builder Tech | Internal — Team | N/A — internal team | Confirmed Stakeholder | N/A | Javon Guerrier | Javon Guerrier |  | Program Director & Instructor | N/A | N/A | N/A | N/A |  |  |  | Confirmed | N/A
Dr. Shawn M. Nicholson | Internal — Team | N/A — internal team | Confirmed Stakeholder | N/A | Javon Guerrier | Dr. Shawn Nicholson |  | Operations Director | N/A | N/A | N/A | N/A |  |  |  | Confirmed | N/A
Explay | Internal — Team | N/A — internal team | Confirmed Stakeholder | N/A | Javon Guerrier | Emanuel Perez |  | Program Designer & Instructor | N/A | N/A | N/A | N/A |  |  |  | Confirmed | N/A
Voltpop | Internal — Team | N/A — internal team | Confirmed Stakeholder | N/A | Javon Guerrier | Andrew Foulks |  | Program Designer & Instructor | N/A | N/A | N/A | N/A |  |  |  | Confirmed | N/A

## Legend
VSU Innovation Program — Stakeholder Map: How to Read This Sheet
Category color key (Stakeholder column fill):
External — Funding | Primarily a cash-funding target (may also have an in-kind ask).
External — In-Kind / Facilitator | Not expected to be a cash source; in-kind support or a connector to other funders.
External — Unscoped | Not yet researched enough to categorize the ask.
Internal — VSU | VSU colleges/centers hosting or co-running the program — not a funding ask, an institutional buy-in ask.
Internal — Team | Confirmed core team members (Builder Tech, Voltpop, Explay, Nicholson).
Research Depth key:
Well-scoped | Named contact, clear stakeholder motivation, and a specific ask already worked out.
In progress / Partial | Some research done, but key gaps remain (e.g. no named contact, or an open confirming question).
Needs work | Little more than a name — motivations and a realistic ask still need to be researched.
Blocked | Cannot move forward until an external condition is resolved (e.g. dean not yet in place).
Confirmed | Internal team member — not applicable.
Note:
All external stakeholders are correctly marked 'Not Yet Contacted' — this is a one-week research sprint to build the target list, not an outreach log. No information from the original working sheet was changed; columns were split/relabeled and rows for the same stakeholder (e.g. Dominion's three contacts) were consolidated for readability.